## Page 1
ISO Annual Schedule Instructions (Quick Start)
If you are new to the ISO role, we recommend keeping it simple. The first and most important thing you need to do is get to know your program. Plan to spend a month looking at each component. Be sure to leave a month open for your IT audit and/or exam. Be aware of any months that could be busy with special projects and build in some flex time.
Components to Schedule | Monthly Activities
• Risk Assessments • Policies • Business Continuity Plan • Vendor Management • Incident Response • Assurance & Testing • Report to the Board • Security Awareness Training | Some activities are time sensitive and need to be managed monthly. We recommend spending time monthly to do activities like: • Send simulated phishing tests • Gather and review vendor due diligence • Run vulnerability scans
ISO Annual Schedule
JANUARY | FEBRUARY | MARCH
APRIL | MAY | JUNE
JULY | AUGUST | SEPTEMBER
OCTOBER | NOVEMBER | DECEMBER

## Page 2
ISO Annual Schedule Instructions
If you're ready to take your ISO schedule to the next level, we recommend following a three-step process to 1) determine the frequency and amount of time needed for each of your activities, 2) set goals on a calendar, and 3) track (and learn from!) your progress. Here's what that could look like. Modify the list of activity to match your needs.
STEP 1: DETERMINE FREQUENCY AND TIME NEEDED For each activity, first identify how many times per year the activity needs to be done (Frequency column). Then identify how long you will need to complete the activity (Weeks Needed column). You will use these numbers to put your activities on a calendar, placing up to four "week" items in a month. Having these numbers will also allow you to add up the total number of weeks of work to determine what reasonably fits in a calendar year. To include margin, consider the year to have 48 weeks (that's 4 weeks per month) instead of the actual 52. This Excel file will calculate the Total Time column for you.
Review and Update Documentation | Frequency (# per year) | Weeks Needed (# per activity) | Total Time (# weeks)
Review Risk Assessments |  |  | 0
Review Policies |  |  | 0
Review Business Continuity Plan (BCP) |  |  | 0
Review Incident Response Plan (IRP) |  |  | 0
Review Vendor Management Program |  |  | 0
Review Cybersecurity Self-Assessment(s) |  |  | 0
Internal and External Testing | Frequency (# per year) | Weeks Needed (# per activity) | Total Time (# weeks)
Test Business Continuity Plan (Exercise) |  |  | 0
Test Incident Response Plan (Exercise) |  |  | 0
Prepare for and Respond to IT Audit |  |  | 0
Prepare for and Respond to Penetration Test |  |  | 0
Prepare for and Respond to Federal / State IT Examination |  |  | 0
Administer Security Awareness Training & Acceptable Use Policy |  |  | 0
Review User Access to Critical Applications |  |  | 0
Other ISO Activities | Frequency (# per year) | Weeks Needed (# per activity) | Total Time (# weeks)
Create & Present Report to the Board |  |  | 0
Coordinate Special Projects |  |  | 0
Attend Conferences / Professional Development |  |  | 0
Go on Vacation & Holidays |  |  | 0
Monthly Activities | Frequency (# per year) | Weeks Needed (# per activity) | Total Time (# weeks)
Perform Vendor Oversight |  |  | 0
Run Vulnerability Scans |  |  | 0
Conduct Simulated Phishing Exercises & Review Report |  |  | 0
Unbooked Weeks
Keep this number above zero, otherwise you will overbook yourself. Overbooking can lead to stress and then burnout for unmet unrealistic expectations. |  |  | 48

## Page 3
ISO Annual Schedule Instructions (continued)
STEP 2: SCHEDULE ACTIVITIES ON A CALENDAR Using your list from step 1, distribute your activities onto an annual calendar to set yourself up for success (see next page). You can always move the activities around as things change, but you can't make more weeks in year.
STEP 3: IDENTIFTY GOALS For each activity, include what "done" looks like. For example, what does it mean to review your risk assessments? Maybe "done" is to have read each one and ensure all your important assets have been included. This may not fit on your one-page calendar, but it could be written out as part of your reminders.
4 Tips To Building a Successful Schedule
We find there are a few things that most people forget when building their schedule for the first time. Here's the list so you can skip these novice mistakes.
Expect the unexpected. | Celebrate milestones.
Do not overbook your month. There is a finite amount of time, and a guarantee of suprises. Life happens and things can throw off your goals and plans. That's expected! Build margin into your schedule for the expected unexpected. Consider the year to be 48 weeks instead of 52. Know that "needing a week" doesn't mean 40 straight hours, but more like 20-30. Account for the time it takes to start and stop, put out fires, and just be human! | You are doing important and remarkable things. Take time to mark them! When you complete your activities across a month, a quarter, a special project, or something similar, throw yourself a party! This can look like a gold star on a chart, going out for coffee with a coworker, having lunch with your team, or finding someone to high-five. When we reward ourselves for our work, our work becomes more rewarding to do.
Use your tools. | Plan for audits and exams.
Your mind is for having ideas, not holding them. Don’t use your brain power to remember your projects and schedule. Instead, use your tools! Create a recurring calendar reminder for the beginning of each month that includes the four (4) activities you will do that month and your goal of "done." | You may not be leading your audits and exams, but you will be replying to request lists and meetings galore. Plan for this disruption by dedicating an activity slot to each audit/exam. Consider what other kinds of "busy seasons" you have in your year that are going to take up space whether you want them to or not.

## Page 4
ISO Annual Schedule |  |  |  | MONTHLY ACTIVITIES • Send Phishing Tests • Gather and Review Vendor Due Diligence • Run Vulnerability Scans
JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE
JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER

## Quick Start Sample
ISO Annual Schedule Instructions (Quick Start)
If you are new to the ISO role, we recommend keeping it simple. The first and most important thing you need to do is get to know your program. Plan to spend a month looking at each component. Be sure to leave a month open for your IT audit and/or exam. Be aware of any months that could be busy with special projects and build in some flex time.
Components to Schedule | Monthly Activities
• Risk Assessments • Policies • Business Continuity Plan • Vendor Management • Incident Response • Assurance & Testing • Report to the Board • Security Awareness Training | Some activities are time sensitive and need to be managed monthly. We recommend spending time monthly to do activities like: • Send simulated phishing tests • Gather and review vendor due diligence • Run vulnerability scans
ISO Annual Schedule
JANUARY | FEBRUARY | MARCH
Security Awareness Training | Business Continuity Plan | Federal IT Exam
APRIL | MAY | JUNE
Risk Assessments | Vendor Management | (family vacation and special projects)
JULY | AUGUST | SEPTEMBER
Incident Response | Report to the Board | Assurance & Testing (User Access Reviews)
OCTOBER | NOVEMBER | DECEMBER
Policies | Annual IT Audit | (holiday activities)

## Frequency Sample
ISO Annual Schedule Instructions
If you're ready to take your ISO schedule to the next level, we recommend following a three-step process to 1) determine the frequency and amount of time needed for each of your activities, 2) set goals on a calendar, and 3) track (and learn from!) your progress. Here's what that could look like. Modify the list of activity to match your needs.
STEP 1: DETERMINE FREQUENCY AND TIME NEEDED For each activity, first identify how many times per year the activity needs to be done (Frequency column). Then identify how long you will need to complete the activity (Weeks Needed column). You will use these numbers to put your activities on a calendar, placing up to four "week" items in a month. Having these numbers will also allow you to add up the total number of weeks of work to determine what reasonably fits in a calendar year. To include margin, consider the year to have 48 weeks (that's 4 weeks per month) instead of the actual 52. This Excel file will calculate the Total Time column for you.
Review and Update Documentation | Frequency (# per year) | Weeks Needed (# per activity) | Total Time (# weeks)
Review Risk Assessments | 1 | 3 | 3
Review Policies | 1 | 3 | 3
Review Business Continuity Plan (BCP) | 1 | 3 | 3
Review Incident Response Plan (IRP) | 1 | 2 | 2
Review Vendor Management Program | 1 | 2 | 2
Review Cybersecurity Self-Assessment(s) | 1 | 1 | 1
Internal and External Testing | Frequency (# per year) | Weeks Needed (# per activity) | Total Time (# weeks)
Test Business Continuity Plan (Exercise) | 1 | 1 | 1
Test Incident Response Plan (Exercise) | 1 | 1 | 1
Prepare for and Respond to IT Audit | 1 | 2 | 2
Prepare for and Respond to Penetration Test | 1 | 1 | 1
Prepare for and Respond to Federal / State IT Examination | 1 | 2 | 2
Administer Security Awareness Training & Acceptable Use Policy | 1 | 1 | 1
Review User Access to Critical Applications | 1 | 1 | 1
Other ISO Activities | Frequency (# per year) | Weeks Needed (# per activity) | Total Time (# weeks)
Create & Present Report to the Board | 4 | 1 | 4
Coordinate Special Projects | 2 | 2 | 4
Attend Conferences / Professional Development | 2 | 1 | 2
Go on Vacation & Holidays | 6 | 1 | 6
Monthly Activities | Frequency (# per year) | Weeks Needed (# per activity) | Total Time (# weeks)
Perform Vendor Oversight | 12 | 0.2 | 2.4
Run Vulnerability Scans | 12 | 0.2 | 2.4
Conduct Simulated Phishing Exercises & Review Report | 12 | 0.2 | 2.4
Unbooked Weeks
Keep this number above zero, otherwise you will overbook yourself. Overbooking can lead to stress and then burnout for unmet unrealistic expectations. |  |  | 1.8

## Full Schedule Sample
ISO Annual Schedule |  |  |  | MONTHLY ACTIVITIES • Send Phishing Tests • Gather and Review Vendor Due Diligence • Run Vulnerability Scans
JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE
Administer Security Awareness Training & AUP Enroll employees. Require completion by 01/31. | Review BCP Review systems/equipment and software. Check for interdependencies. | IT Exam Respond to request list items. | Attend Conferences Tandem KEYS Conference | Report to the Board Prepare for and present quarterly report. | Personal Time Family Vacation
Report to the Board Prepare for and present quarterly report. | Review BCP Coordinate with department heads. Review emergency locations and checklists. | IT Exam Be available for on-site visit and meetings. | Risk Assessments Review critical assets. | Vendor Management Review policy and program. Confirm all vendors are included. | Special Projects Research AI / emerging technology for business.
Monthly Activities | Test BCP Schedule tabletop exercise. | Personal Time Spring Break with Family | Risk Assessments Review threats. Address current risks. | Vendor Management Include recent guidance best practices. | Monthly Activities
Review BCP Review business processes. Update Business Impact Analysis (BIA). | Monthly Activities | Special Projects Security team meeting. Respond to findings. End of quarter reporting. | Risk Assessments Review mitigating controls. | Monthly Activities | Special Projects Security team meeting. End of quarter reporting.
JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
Report to the Board Prepare for and present quarterly report. | Test IRP Schedule tabletop exercise. | Personal Time Life Event (e.g., childbirth, weddings, anniversary trips, care for parents, etc.) | Monthly Activities | Report to the Board Prepare for and present quarterly report. | Monthly Activities
Incident Response Plan Review policy and program. | Cybersecurity Assessment Review cybersecurity self-assessments. | Assurance & Testing Penetration Test | Policies Read through policies and confirm accuracy. | IT Audit Respond to request list items. | Assurance & Testing User Access Review
Incident Response Plan Confirm all incidents were adequately documented. | Attend Conferences ISACA GRC Conference | Monthly Activities / Special Projects Prepare for Cybersecurity Awareness Month (Oct.). | Policies Review meeting minutes from committee/teams. | IT Audit Be available for on-site visit and meetings. | Special Projects Security team meeting. Respond to findings. End of quarter reporting.
Monthly Activities | Monthly Activities | Special Projects Security team meeting. Respond to findings. End of quarter reporting. | Policies Update revision dates. Create follow-up tasks. | Monthly Activities / Personal Time Holidays with Family | Personal Time Holidays with Family